## Planned Feature Status
Feature Name	Status	Responsible	Rem. hrs. pre-QA	Feature Detail	Blocking Issues	Feature Notes

Refresh browser using async received screen description.	Prototyping; Completion goal: 02/03/12	Max		App engine tells Pushy "refresh, and display this screen [X]" The X is some abstract interactive specification for a screen with related behavor.		JS code from default.html will be moved to separate .js files to manage associated behavior rules; same with CSS to manage associated appearance

Process abstract interactive screen description and render to web client.	Prototyping; Completion goal: 02/03/12	Max		This description is supplied using JVM objects - do not define a document format in XML.
Basic structure of GUI	Committed to Friendularity 01/28/12	Max		Outline of "empty" div elements with change rules; written on Liftweb Framework
Sound FX	Prototyping HOLD; see Feature Notes	Max		Sound effects applied to actions in GUI of web app.	Cannot find suitable audio material under proper licensing for enterprise usage. May require in-house production of audio materials.	Have access to pro recording equip + analog synths; can record quality sounds in a matter of hours. Could solve issue of future needs for GUI sounds to be used in-house?