## Planned Feature Status
Feature Name	Status	Responsible	Rem. hrs. pre-QA	Feature Detail	Blocking Issues

Refresh browser using async received screen description.	Prototyping	Max		App engine tells Pushy "refresh, and display this screen [X]" The X is some abstract interactive specification for a screen with related behavor.

Process abstract interactive screen description and render to web client.	Prototyping	Max		This description is supplied using JVM objects - do not define a document format in XML.
Basic structure of GUI	Committed to Friendularity 01/28/12	Max		Outline of "empty" div elements with change rules; written on Liftweb Framework
Sound FX	Prototyping	Max		Sound effects applied to actions in GUI of web app.	Cannot find suitable audio material under proper licensing for enterprise usage. May require in-house production of audio materials.