## Planned Feature Status
Feature Name	Status	Responsible	Rem. hrs. pre-QA	Feature Detail	Blocking Issues	Feature Notes

Refresh browser using async received screen description.	Prototyping; Completion goal: 02/03/12	Max		App engine tells Pushy "refresh, and display this screen [X]" The X is some abstract interactive specification for a screen with related behavor.		JS code from default.html will be moved to separate .js files to manage associated behavior rules; same with CSS to manage associated appearance

Process abstract interactive screen description and render to web client.	Prototyping; Completion goal: 02/03/12	Max		This description is supplied using JVM objects - do not define a document format in XML.
Basic structure of GUI	Committed to Friendularity 01/28/12	Max		Outline of "empty" div elements with change rules; written on Liftweb Framework
Sound FX	Prototyping HOLD; see Feature Notes	Max		Sound effects applied to actions in GUI of web app.	Cannot find suitable audio material under proper licensing for enterprise usage. Will require properly licensed audio materials if sound effects are to be used for this webapp.